## Sheet1
Task Management
# | Ticket No | Project Name | Module Name | Calls/Task | Status | Task Descriprion | Document | Action
1 | 28-05-2024 TIC-202405-0061 | Zigma - Task Manager | Test | Normal New Task | Pending | testingg
2 | 23-05-2024 TIC-202405-0057 | Presentation work | Presentation | Normal New Task | Pending | UI - Design
3 | 23-05-2024 TIC-202405-0058 | Zigma Software - Task Manager | Entry/Report | Normal New Task | Pending | Task details to display - Ticket Assign
4 | 23-05-2024 TIC-202405-0059 | Zigma Software - Task Manager | Entry/Report | Normal Additional | Pending | Need comments and remarks while starting the task - Ticket Assign
5 | 23-05-2024 TIC-202405-0060 | Zigma Software - Task Manager | Entry/Report | Normal Correction | Pending | Ticket Creation - image upload
6 | 22-05-2024 TIC-202405-0053 | Zigma Software - Task Manager | Entry/Report | Normal Additional | Pending | Ticket Assign Module
7 | 22-05-2024 TIC-202405-0054 | Presentation work | Presentation | Normal New Task | Pending | Zigma current task PPT preparation
8 | 22-05-2024 TIC-202405-0055 | Zigma ERP | EHS | Normal New Task | Pending | EHS Bioculture Stock Report
9 | 22-05-2024 TIC-202405-0056 | Zigma ERP | EarthMovers | Normal Bug | Pending | Act Hours diff shown in Indvidual vehicle report and Running hrs report for TN28AA3469 on Apr24.
10 | 21-05-2024 TIC-202405-0049 | Zigma Software - Task Manager | Entry/Report | Normal Additional | Pending | Ticket Taken update form the data to be display accordingly
11 | 21-05-2024 TIC-202405-0050 | BP D2D Waste Management | UI Design | Normal New Task | Pending | Theme searching and installation
12 | 21-05-2024 TIC-202405-0051 | Software Training | Training | Normal New Task | Pending | JS
13 | 21-05-2024 TIC-202405-0052 | BP D2D Waste Management | UI Design | Normal New Task | Pending | Field work
14 | 20-05-2024 TIC-202405-0047 | Zigma - Task Manager | Ticket entry / Report | Normal Additional | Pending | Impact type option moving from g_test to g_admin - Master form, Filter and update form user name update option.
15 | 20-05-2024 TIC-202405-0048 | Zigma - Test | Test | Normal Additional | Pending | Staff portal - validation need for exam taken
16 | 18-05-2024 TIC-202405-0044 | Zigma ERP | EHS | Normal New Task | Pending | One of the Checklist for HO EHS Engineer. Remodify Bio culture and Deodorizer form as per user requirements
17 | 18-05-2024 TIC-202405-0045 | Zigma - Task Manager | Ticket entry / Report | Normal New Task | Pending | Multi document upload in sublist
18 | 18-05-2024 TIC-202405-0046 | Presentation work | Presentation | Normal New Task | Pending | Process flow of BSF
19 | 17-05-2024 TIC-202405-0038 | Zigma - Task Manager | Dashboard | Normal Bug | Pending | The site-wise bar chart for a few sites in the print view is not displaying correctly
20 | 17-05-2024 TIC-202405-0039 | BP D2D Waste Management | UI Design | Normal New Task | Pending | D2D Waste Management UI Design Work
21 | 17-05-2024 TIC-202405-0040 | Zigma - Test | Test | Normal New Task | Pending | Modification the admin panel
22 | 17-05-2024 TIC-202405-0041 | Zigma - Website (zigma.in) | Front End | Normal New Task | Pending | Zigma Website Design
23 | 17-05-2024 TIC-202405-0042 | Zigma - Task Manager | Test | Normal Additional | Pending | Priority creation need to add active inactive status
24 | 17-05-2024 TIC-202405-0043 | Zigma - Task Manager | Ticket entry / Report | Normal Additional | Pending | Complain creation for update based on impact type
25 | 16-05-2024 TIC-202405-0035 | Zigma ERP | Sales | Normal New Task | Pending | In Confirmation of receipt approval Form Filter date to be freeze
26 | 16-05-2024 TIC-202405-0036 | Zigma ERP | Sales | Normal New Task | Pending | In Freight creation Form Filter date to be freeze
27 | 16-05-2024 TIC-202405-0037 | Zigma ERP | Admin/Master | High New Task | Pending | Lumshnong, Meghalaya 793210 ULB distance checking
28 | 15-05-2024 TIC-202405-0031 | Zigma Software - Task Manager | Entry/Report | Normal Bug | Pending | Ticket Taken worked hours timing is calculating wrongly
29 | 15-05-2024 TIC-202405-0032 | Zigma Software - Task Manager | Entry/Report | Normal New Task | Pending | EMP Wise Daily Report
30 | 15-05-2024 TIC-202405-0033 | Zigma Payroll | Employee Attendance | High Bug | Pending | From May1 many Erode Ho Employees attendance Not shown. pls do needful
31 | 15-05-2024 TIC-202405-0034 | Zigma Software - Task Manager | Admin/Master | Normal New Task | Pending | Dashboard
32 | 14-05-2024 TIC-202405-0001 | Zigma ERP | Store | High New Task | Pending | Rate contract form
33 | 14-05-2024 TIC-202405-0002 | Zigma ERP | EarthMovers | High New Task | Pending | Vehicle Document Entry
34 | 14-05-2024 TIC-202405-0003 | Zigma ERP | Sales | High New Task | Pending | New log-sheet revision
35 | 14-05-2024 TIC-202405-0004 | Zigma ERP | Sales | High Additional | Pending | Co Processing Certificate Online upload and Approval
36 | 14-05-2024 TIC-202405-0005 | Zigma ERP | Sales | High New Task | Pending | Payable / Receivable online entry and Approval
37 | 14-05-2024 TIC-202405-0006 | Zigma ERP | Sales | High New Task | Pending | Other aggregate quotation online upload and approval
38 | 14-05-2024 TIC-202405-0007 | Zigma ERP | Sales | High New Task | Pending | RDF transporter quotation online upload and approval
39 | 14-05-2024 TIC-202405-0008 | Zigma ERP | Sales | High New Task | Pending | Trigger mail should be sent to the customer every Tuesday. Reg -Quality Analysis Report.
40 | 14-05-2024 TIC-202405-0009 | Software Training | Training | Normal New Task | Pending | Software Training for new joiners
41 | 14-05-2024 TIC-202405-0010 | Zigma ERP | Sales | High Bug | Pending | Duplicate tickets and Duplicate DCs are generated
42 | 14-05-2024 TIC-202405-0011 | Zigma ERP | WB Portal | High New Task | Pending | Makarpura disposal data to be added
43 | 14-05-2024 TIC-202405-0012 | Zigma ERP | WB Portal | High New Task | Pending | Guwahati disposal data to be added
44 | 14-05-2024 TIC-202405-0013 | Zigma ERP | WB Portal | High New Task | Pending | Nagpur disposal data to be added
45 | 14-05-2024 TIC-202405-0014 | Zigma ERP | Accounts | Normal Additional | Pending | Journal entry debit note option need to be added
46 | 14-05-2024 TIC-202405-0015 | Zigma Software - Task Manager | Entry/Report | Normal Additional | Pending | Ticket Taken list form field adding
47 | 14-05-2024 TIC-202405-0016 | Zigma Software - Task Manager | Entry/Report | Normal Additional | Pending | Ticket Assign form in list field like Project/Module, Main Task/Sub Task, Staff name to be added
48 | 14-05-2024 TIC-202405-0019 | Zigma Software - Task Manager | Entry/Report | Normal New Task | Pending | Ticket Assign add form - Ticket no drop down need to add project name.
49 | 14-05-2024 TIC-202405-0020 | Zigma Software - Task Manager | Entry/Report | Normal Correction | Pending | Ticket Assign on insert module name need to check
50 | 14-05-2024 TIC-202405-0021 | Presentation work | Presentation | High New Task | Pending | Zigma Miyawaki forests design
51 | 14-05-2024 TIC-202405-0022 | Zigma Software - Task Manager | Admin/Master | Normal Bug | Pending | Ticket Creation - Project name is showing disable
52 | 14-05-2024 TIC-202405-0023 | Zigma Software - Task Manager | Entry/Report | Normal Additional | Pending | Task Report
53 | 14-05-2024 TIC-202405-0024 | Zigma Software - Task Manager | Entry/Report | Normal New Task | Pending | Ticket creation and Ticket Assign Filter not working
54 | 14-05-2024 TIC-202405-0025 | Zigma - Task Manager | Dashboard | High Bug | Pending | Action Not Taken on click print data is not listing
55 | 14-05-2024 TIC-202405-0026 | Zigma ERP | WB Portal | High Bug | Pending | Puducherry site WB Tickets - Images not shown for April24 & May24
56 | 14-05-2024 TIC-202405-0027 | Zigma - Test | Test | Normal New Task | Pending | Online test portal creation
57 | 14-05-2024 TIC-202405-0028 | Zigma Software - Task Manager | Admin/Master | Normal New Task | Pending | Dashboard work
58 | 14-05-2024 TIC-202405-0029 | Presentation work | Presentation | High New Task | Pending | Makarpura PPT in canva (requested by Nagesh sir)
59 | 14-05-2024 TIC-202405-0030 | Zigma ERP | WB Portal | High Additional | Pending | BSF Kochi WB Portal integration